## Sprint Tracker
# | Item | Component | Phase | Dependencies | Acceptance Criteria | Owner Persona | Status | Start Date | Target Date | Actual Date | Blockers | Notes
1 | Build parse_identity.py with UTF-8 BOM handling and stable JSON output | parse_identity.py | NOW | None — start here | Extracts source_id from frontmatter; handles BOM; returns structured JSON on success and failure | Data Engineer | Not Started
2 | Update validator_runner.py to use parse_identity.py as parser authority | validator_runner.py | NOW | Item 1 | Imports parse_identity; no duplicate regex; distinct exit codes for full 0-5 contract (APPROVE/REJECT/ESCALATE/SCHEMA_FAULT/SYSTEM_FAULT/TOKEN_OVERFLOW) | Backend Engineer | Not Started
3 | Update Run-Validator.ps1 to build transaction keys from parser output | Run-Validator.ps1 | NOW | Items 1, 2 | Context digest computed; ledger keys use canonical form; startup reconciliation persists immediately | Data Engineer | Not Started
4 | Create validation_result.schema.json | Schema artifact | NOW | None — parallel with Item 1 | Covers approve/reject/escalate outcomes; validator_runner validates output against it | Backend Engineer | Not Started
4b | Create ops/validator_config.json (model configuration manifest) | Config artifact | NOW | LLM provider decision (Open Question #1) | Contains all 9 fields (provider, model_id, quantization_level, temperature, top_p, max_context_tokens, system_instruction_hash, lora_adapter_path, tokenizer_id); all fields except tokenizer_id included in context digest | AI/ML Architect | Not Started |  |  |  | Blocked by Open Question #1
4c | Implement JSON-structured logging (JSONL) | Run-Validator.ps1 | NOW | None — parallel with Item 1 | Heartbeat + transaction entries; Try/Catch wrapper on top-level loop; SYSTEM_FAULT exits write to error log | Data Engineer | Not Started
4d | Token budget enforcement in validator_runner.py | validator_runner.py | NOW | Item 4b (model config) | Pre-send token count; policy_bundle + article must fit model context window; overflow handled as non-terminal skip (EXIT_TOKEN_OVERFLOW code 5) | AI/ML Architect | Not Started
4e | Bootstrap golden corpus: curated examples covering approve/reject/escalate + adversarial edge cases | Test artifact | NOW | None — parallel with Item 1 | Mixed-source: manually curated + synthetic adversarial; overrepresents malformed frontmatter, policy conflicts, near-limit tokens, ambiguous cases | QA/Test Lead | Not Started
4f | Runtime parity harness: managed vs. self-hosted agreement testing on golden corpus | Test harness | NOW | Items 2, 4b, 4e | Both model paths evaluate same corpus; decision agreement rate computed; threshold gates self-hosted activation | AI/ML Architect | Not Started
5 | Build Promote-ToVerified.ps1 with namespace preservation and tree SHA verification | Promote-ToVerified.ps1 | NEXT | Items 1-4 complete | Mirrors provisional path under verified/; verifies remote PR equivalence via tree SHA; full workspace rollback on fast-path | DevOps | Not Started
6 | Build _policy_bundle.md v1 with initial content policy rules | policy_engine/ | NEXT | Product sign-off on policy criteria | Covers accuracy, completeness, and formatting standards for wiki articles | Product Manager | Not Started
7 | End-to-end test suite: T1-T8 test matrix | Test harness | NEXT | Items 1-6 | All 8 test matrix scenarios (T1-T8) pass including declined PR lifecycle and frontmatter injection | QA/Test Lead | Not Started
7b | Self-hosted inference stack evaluation: vLLM vs. TGI vs. llama.cpp | Infrastructure | NEXT | Item 4b, parity harness results | Evaluate FlashAttention/PagedAttention support, KV cache ceiling, max concurrency per GPU, quantization quality matrix | AI/ML Architect | Not Started
7c | Quantization evaluation: FP16 vs. Q8 vs. Q4_K_M on golden corpus | Evaluation artifact | NEXT | Items 4e, 4f, 7b | Measure decision agreement rate vs. managed API at each quantization level; document quality/cost trade-off | AI/ML Architect | Not Started
8 | Rejection feedback sidecar files for content authors | P1 feature | LATER | Core pipeline operational | Write structured feedback to provisional/ alongside rejected drafts |  | Not Started
9 | Pipeline metrics dashboard (throughput, latency, rejection rate) | P1 feature | LATER | Ledger data available | Read-only view of validation_state.json for operational visibility |  | Not Started
10 | Vertex AI regime classification integration | P2 feature | LATER | Runner model config externalized | Requires model provider abstraction in validator_runner.py |  | Not Started
11 | Fine-tuning decision gate: prompt-only vs. fine-tuned accuracy | Evaluation | LATER | 500+ human-reviewed transactions | If fine-tuned model exceeds prompt-only by >5% agreement on holdout, proceed to LoRA/QLoRA adaptation |  | Not Started
12 | LoRA/QLoRA fine-tuning on pipeline evaluation data | Model adaptation | LATER | Item 11 decision gate passes | Train LoRA adapter on human-reviewed outcomes; merge into self-hosted model; re-run parity harness |  | Not Started
13 | DPO alignment from PR review outcomes | Model adaptation | LATER | Item 12 complete; reviewer merge/decline data | Train on preference pairs (merged PR = positive, declined PR = negative) |  | Not Started
14 | Rolling holdout set: frozen evaluation slice refreshed on cadence | Evaluation infrastructure | LATER | Production corpus sufficiently large | Immutable holdout prevents overfitting; used only for parity testing and regression detection |  | Not Started

## Summary
LLM-Wiki Content Pipeline — Sprint Summary
Metric | NOW | NEXT | LATER
Total Items | 9 | 5 | 7
Not Started | 9 | 5 | 7
In Progress | 0 | 0 | 0
Complete | 0 | 0 | 0
Blocked | 0 | 0 | 0

## Open Questions
# | Question | Owner | Blocking | Status | Resolution | Date Resolved
OQ-1 | Which managed API provider is the primary evaluation path for v1, and which self-hosted model/serving stack is the parity candidate? | Engineering + Product | Items 2, 4b, 4d, 4f | Open
OQ-2 | What is the Gitea branch protection configuration? | Engineering / Infra | Item 5 (Promote-ToVerified.ps1) | Open
OQ-3 | Sidecar feedback format and delivery mechanism | Product | Item 8 | Open
OQ-4 | Rate limit guardrails for managed API | Engineering | Items 2, 4d | Open